## Slide 1: IdentityIQ Upgrade Recommended Practices
General Guidelines and Planning
Mike Bauer, Professional Services Manager

## Slide 2: Agenda
Plan
Versions: IdentityIQ and Supporting Software
Environments
Version Control System
Build Process
What objects need manually upgraded
What can go wrong during upgrade
System Backups: Database and File System

## Slide 3: Plan – High Level Guidelines
  Upgrades should be fast, inexpensive and easy
    Build a better methodology and framework for future upgrade simplification
  Customization is your enemy
    Moving towards OOTB solutions and best practices to reduce bloat/complexity
  Put the word “Practical” in front of all considerations

## Slide 4: Plan – 4 main goals
  SSB/SSD/code refresh - Deprecation checker, refresh config objects
  Treat it as spring cleaning - update design/test materials, code base, platforms, change management process
  Biggest part of the upgrade is regression testing and cleaning up any eFixes from prior issues, that drives majority of scope
  Allow for time to learn about new features and improvements to incorporate into your solution. Don’t just upgrade to avoid end of life

## Slide 5: Plan
  Follow the best practices white paper
    There is an entire packet of free materials around upgrades on Compass!
  Develop a migration plan
    Review your platforms for infrastructure updates
    Create a listing of customized code base
      What was changed and why
      Is there an out of box feature or enhancement that can replace this customization
      Does this object need regression tested?
      Deprecation Check via SSD!
    Follow release notes and installation product documentation
      Could be missing steps that are not typical
    Create a run book for the upgrade steps

## Slide 6: Versions
  Need to step through every major release
    6.3p4 -> 6.4 -> 7.0 -> 7.1 -> -> 7.2 -> 7.3 -> 8.0 -> latest patch
    Apply database schema changes
    Run upgrade scripts
  Once desired version is upgraded
    Apply desired patch level
    Start application (no need to start it before now)
    Export XML objects
      Persist in Source Control since these objects may have changed
    Re-apply any customizations to the latest OOB files
    Regression test functionality to determine whether API changes affected the code base

## Slide 7: Other Software Versions
  IQService - Should be latest from product
  Connector Gateway - Should be latest from product
  Review the supported platforms matrix
    https://community.sailpoint.com/docs/DOC-3183
  Try to get on latest supported versions
    Java
    Application Server
    Database
    Database Driver
    Operating System

## Slide 8: Environments
  Sandbox
    Most likely will rebuild with new version
  Development
    Practice here first and get updated objects
    Start regression testing of code base
  QA
    This should be a snapshot of the production database to practice the upgrade
    Run regression testing on this data set
  Staging
    Similar to QA
  Production
    The ideal scenario is to have no surprises when you get here
  DR, Reporting, Role Mining
    Like above, do the non-essential path systems once Staging is complete, or after Prod

## Slide 9: Version Control System
  XML Objects
    All objects could be modified by the upgrade process, so extracting the modified objects and persisting them to your version control system will help ensure a repeatable build process
  Configurations
    Most of these object types use the merge import action
  Source Code
    Java
    Also, BeanShell related objects like workflows and rules
  File System Changes
    Branding

## Slide 10: Build Process
  SSB
    Has a new features and is getting better
    Many tools that can help establish a repeatable build process
  Continuous Integration
    Can help reduce the amount of regression testing time

## Slide 11: What objects need manually upgraded
Check release notes for API changes. Not all are included.
Regression testing is often the only way to verify your objects.
  Workflows
    Port customizations to new OOB workflows to take advantage of new features and enhancements
      For example, step replicator in workflow
  Rules
  Rule Libraries
  Java
  File system changes

## Slide 12: What happens during upgrade
  upgrade_identityiq_tables.<db type>
    Shows database schema changes
      Added and removed tables and columns
      Added and removed indexes
  upgrade.xml
    Shows executables and tasks
      Verbose names are descriptive of what action is being taken
    May include a refresh task where threads can be increased
  upgradeObjects.xml
  upgradeObjects-lcm.xml

## Slide 13: What can go wrong during upgrade
  Data Corruption
    IDX
  File system
    E-fixes not removed
    Modifications not applied to latest OOB versions
  XML objects and source code
    API changes, deprecations
  Incomplete documentation
    Ensure Design and Test Cases are fully in sync with current Prod build

## Slide 14: System Backups
  Database Backups
    Make sure to backup the data before executing the upgrade
    Restore point on data if things are going as planned
  File System Backups
  Be sure to retest your BCP/DRP plans and data backup processes